## Slide 1
Infrastructure and Installation
Project schedule
2nd HIE ISOLDE Management meeting
CERN, 29 June 2012
HIE-ISOLDE
Erwin Siesling

## Slide 2
Abstract
  HIE-ISOLDE – integration
  Civil Engineering, Main Services and Cryogenics
  Tunnel and Superconducting Linac
  High Energy Beam Transfer line
  Urgent issues:
  Civil Engineering 1 ½ month delay
  Heat dissipation and power consumption
  Cryo Line – modular installation
  Linac and HEBT cabling solutions
  HEBT dipole power convertor racks

## Slide 3
Hie-Isolde Planning
Hie-Isolde installation planning in EDMS:
Projects – Accelerators - Hie-Isolde – Infrastructure & Integration - Planning
https://edms.cern.ch/nav/P:CERN-0000072786:V0/P:CERN-0000090679:V0/TAB3

## Slide 4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
2011
2012
2013
2014
2015
2016
Civil
Main services
Cryo
CM 1&2
CM 3&4
5.5MeV/u
10MeV/u
Beam Transfer Line
CM 5&6
Hie-Isolde Planning
  Activities until LS1: Civil Engineering & Main Services
Dec 2012 - Apr 2014
sd
sd
sd
CM1&2
Isolde & REX Ops
shutdown
LS1
Cryo Mod 1 & 2 install
(Isolde normal operations)
(REX perturbations)
Timeline:
sd
Ventilation
Demi water
Electrical syst.s
Start LS1
3 dec 2012

## Slide 5
Until LS1
GS/SE : DANIEL PARCHET, ELISEO PEREZ-DUENAS
Civil Engineering
LS1

## Slide 6
LS1
Buildings ready October:
End Sept: roof & isolation installed
End Oct: metal structures in place
Delay 1 ½ month
Until LS1
GS/SE : DANIEL PARCHET, ELISEO PEREZ-DUENAS
Civil Engineering

## Slide 7
Civil Engineering
27 June: outer walls 1st floor B199, first wall B198

## Slide 8
Civil Engineering
Compressor and Cold Box Building
Civil Engineering finished summer 2012
Autumn 2012 !

## Slide 9
Main Services
Electrical systems, Cooling & Ventilation
Start installation Main Services Oct 2012

## Slide 10
LS1
Buildings ready October:
End Sept: roof & isolation installed
End Oct: metal structures in place
Delay 1 ½ month
Into LS1
GS/SE : DANIEL PARCHET, ELISEO PEREZ-DUENAS
Civil Engineering

## Slide 11
Electrical systems
Electrical systems: Oct 2012 – June 2013

## Slide 12
Racks sub systems
Courtesy: Stephane Maridor

## Slide 13
Racks sub systems
URGENT: For the different equipment:
CV: heat dissipation to air and water
EL: power consumption
32kW (str & quads) + 70kW (dipl) = 102 kW air

## Slide 14
Faraday Racks
Courtesy: Stephane Maridor / Daniel Valuch

## Slide 15
Cold air inlet
Hot air exhaust
Cold air inlet
Hot air exhaust
Faraday Racks

## Slide 16
Cooling & Ventilation
EN/CV : PAUL PEPINSTER, BENOIT LACARELLE
LS1
Start of LS1:
3 dec - Keydate!
Buildings ready October:

## Slide 17
Cooling & Ventilation
EN/CV : PAUL PEPINSTER, BENOIT LACARELLE
LS1
Point of No Return!

## Slide 18
Cooling & Ventilation
Cooling & Ventilation: Oct 2012 – June 2013

## Slide 19
Ventil units
Cooling & Ventilation
Ventil units
Cooling pumps
Cooling & Ventilation: Oct 2012 – June 2013

## Slide 20
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
2011
2012
2013
2014
2015
2016
Civil
Main services
Cryo
CM 1&2
CM 3&4
5.5MeV/u
10MeV/u
Beam Transfer Line
CM 5&6
LS1 into 2014 run
Dec 2012 - Apr 2014
sd
sd
sd
CM1&2
Isolde & REX Ops
shutdown
LS1
Cryo Mod 1 & 2 install
(Isolde normal operations)
(REX perturbations)
Timeline:
sd
Ventilation
Demi water
Electrical syst.s
  Activities LS1 into 2014 run: Cryogenics, Beam transfer Line, Cryo Modules, commissioning
End LS1:Start Low E physics apr 2014

## Slide 21
Cryogenics
TE/CRG : NICOLAS DELRUELLE, JOS METSELAAR
LS1
CM1&2
LS1 into 2014 run

## Slide 22
Cryogenics
Compressors: July 2013 – December 2013
Cold Box: Jan 2014 – June 2014

## Slide 23
Tunnel and Cryo Line
Installation tunnel: Sep 2013 - LS1
Cryo Cold Line: January 2014 – June 2014

## Slide 24
Tunnel

## Slide 25
Tunnel
Cable feedthrough and He release

## Slide 26
Tunnel- RF cabling

## Slide 27
Tunnel
Cable feedthrough and He release also via niche
Safety aspects: Ana-Paula Bernardes EN/STI

## Slide 28
SC Linac, Cryo- & Beamline
Modular installation
HIE ISOLDE Superconducting Linac
High Energy Beam Transferline

## Slide 29
Modular installation
Courtesy: Matteo Pasini, Matthew Fraser
Schematic:
2014
5.5MeV/u
2016
10MeV/u
>2017

## Slide 30
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
2011
2012
2013
2014
2015
2016
Civil
Main services
Cryo
CM 1&2
CM 3&4
5.5MeV/u
10MeV/u
Beam Transfer Line
CM 5&6
Dec 2012 - Apr 2014
sd
sd
sd
Isolde & REX Ops
shutdown
LS1
Cryo Mod 1 & 2 + HEBT install (Isolde running)
Timeline:
sd
Ventilation
Demi water
Electrical syst.s
End LS1:Start Low E physics as of apr 2014
CM 1 & 2 and beamline
HEBT & Linac commissioning
hardware sept.2014
beam oct.2014
  Activities into 2014 run: Cryo Modules 1 &2 and Beam transfer Line

## Slide 31
TE/MSC: JEAN-PHILIPE TOCK, YANN LECLERCQ, LLOYD WILLIAMS, ARNAUD BOUZOUD
First High-β Cryo Module

## Slide 32
Superconducting Linac
TE/MSC: JEAN-PHILIPE TOCK, YANN LECLERCQ, LLOYD WILLIAMS, ARNAUD BOUZOUD
LS1

## Slide 33
Superconducting Linac
LS1
CM1&2
TE/MSC: JEAN-PHILIPE TOCK, YANN LECLERCQ, LLOYD WILLIAMS, ARNAUD BOUZOUD

## Slide 34
Modular Linac & Cryo Line
Cryo Cold Line- stage 1: January 2014 – June 2014
2014
5.5MeV/u
Linac CM 1&2 - stage 1: August 2014 – October 2014
Courtesy: Stephane Maridor

## Slide 35
Cryo Cold Line- stage 2a
2016
10MeV/u
Modular Cryo Line
Linac CM High-β 1,2,3&4 - stage 2a
Courtesy: Stephane Maridor

## Slide 36
>2017
Cryo Cold Line- stage 2b
Modular Cryo Line
Linac CM High-β 1,2,3&4 + Low-β 1&2 - stage 2b
Courtesy: Stephane Maridor

## Slide 37
High Energy Beam Tranfer

## Slide 38
Beam Transfer Line
EN/HDO : YACINE KADI, TE/EPC: DAVID NISBET, TE/MSC: JEREMIE BAUCHE, TE/ABT: BRENNAN GODDARD, BE/OP: DIDIER VOULOT
LS1

## Slide 39
Beam Transfer Line
LS1

## Slide 40
Straight line with 2 branches – Oct 2013 - Sept 2014
Miniball move: Oct 2013 – April 2014
Miniball
Beam diagnostics
Exp.
Station 1
Miniball
HEBT Stage 1
Exp.
Station 2

## Slide 41
Miniball
TSR
Stage 3: TSR and beyond..
Next stages
Stage 2: The bend and 3rd Experiment station – 2016?
With HELIOS and Miniball occupying the two stations the bend will be in high demand
Steel frame work with
Magnetic shielding
approx size
5.5mL x 3.75 mW x 3 mH
Helios
12 Tons
Exp.
Station 3

## Slide 42
Floor spacing
Increase experimental floor space by moving all power convertor racks onto existing platform

## Slide 43
HEBT Stage 1
Transport zone
Large dipole EPC racks
Cable trays
Collisions
Courtesy: Stephane Maridor

## Slide 44
Linac & HEBT Infrastructure
Infrastructure:
electrical (power, signals & controls)
cooling water
compressed air
N2 venting line
vacuum exhaust line

## Slide 45
30 power-concert. racks
5 vac. racks
2 b.i. racks(+3)
4 WIC racks
Electric. Dist. racks
Cabling solution version 1
Courtesy: Stephane Maridor

## Slide 46
7x cables trays (200x100)
Cabling solution version 1
Courtesy: Stephane Maridor

## Slide 47
2x 4 cables trays (500x100)
7x cables trays (200x100)
Cabling solution version 1

## Slide 48
Cables trays under racks
False floor in tunnel
Concrete duct
Cabling solution version 2

## Slide 49
750mm
Cabling solution version 2

## Slide 50
Cabling solution version 2
Radiation issues?: Ana-Paula Bernardes EN/STI

## Slide 51: Dipoles need larger power converter racks
1-Version rack DIPOLE “PC”(width 600 MM ) – preferred
500A : 3x600 ; 250A : 2x600
Space: 7x1.8m + 2x1.2m = 15m
2-Version rack DIPOLE “PC”(width 800 MM )
500A : 2x800 ; 250A : 1X800
Space: 7x1.6m + 2x0.8m = 12.8m
Before:
30x0.6m=18m – all on platform
Now:
20x0.6m=12m (steerers & quads)
+ 15m (version 1 – preferred) or 12.8m (version 2)
HEBT Dipole EPC racks

## Slide 52
Situation before larger racks
HEBT Dipole EPC racks

## Slide 53
7x3 RACKS “PC” 500A
2x2 RACKS “PC” 250A
DIPOLES
20 RACKS “PC”
QUAD/STEERER
HEBT Dipole EPC racks
Racks version 1 = 15m
Courtesy: Stephane Maridor

## Slide 54
HEBT Dipole EPC racks
Racks version 1 = 15m

## Slide 55
1
HEBT Dipole EPC racks
Racks version 1 = 15m
Restrictions on the platform:
CV -> needs new duct to bring in air: to air 102kW total (70kW from dipoles
EPC -> maintenance and intervention difficult. Heavy equipment
Needs displacement of the staircase
Spacing is a serious issue for version 1 (preferred)
Re-calculate weight for platform

## Slide 56
1
HEBT Dipole EPC racks
Racks version 1 = 15m

## Slide 57
2
HEBT Dipole EPC racks
Racks version 2 = 12.8m

## Slide 58
HEBT Dipole EPC racks
Racks version 2 = 12.8m
Restrictions on the platform:
CV -> needs new duct to bring in air: to air 102kW total (70kW from dipoles
EPC -> maintenance and intervention difficult. Heavy equipment
Needs displacement of the staircase
Re-calculate weight for platform

## Slide 59
Acknowledgement
GS/SE : DANIEL PARCHET, ELISEO PEREZ-DUENAS
EN/MEF : STEPHANE MARIDOR, ELEFTHERIOS ZOGRAFOS
BE/ABP : FREDERIK WENANDER
BE/OP : DIDIER VOULOT
PH/SME : YORICK BLUMENFELD
EN/HDO : YACINE KADI
BE/RF : MATTEO PASINI, MATTHEW FRASER, DANIEL VALUCH, WALTER VENTURINI, LUCA ARNAUDON
EN/CV : PAUL PEPINSTER, BENOIT LACARELLE
EN/EL : RENE NECCA
TE/CRG : NICOLAS DELRUELLE, JOS METSELAAR
EN/STI : RICHARD CATHERALL, ANA-PAULA BERNARDES
GS/DI : CYRILLE BEDEL
TE/MSC : JEAN-PHILIPE TOCK, YANN LECLERCQ, LLOYD WILLIAMS, ARNAUD BOUZOUD
TE/ABT : BRENNAN GODDARD

## Slide 60
Thank you for your attention

## Slide 61
HIE-Isolde. RF system configuration per cavity